## Summary
Purpose | The purpose of this workbook is to collect and document information necessary and relevant to complete the preimplemenation and implementation project phases of Your Specific Project: ___________________________________________________________
Account Information
Hospital(s)/Testing Site
City
State
Contact Name(s) | Department/Resource | Email

## Implementation Plan
Analyzer & Software Implementation Plan
Roles and Responsibilities*
Phase | Activity | V PM | V OS | V IT | Customer
Pre Installation | Weekly communication begins | R | P | P | P
| Project development | R | I | I | P
| Deliver project plan | R | I | I | I
| Security documents | I | I | R | R
| Server discovery discussion | I | I | R | P
| Middleware discussion | I | I | R | R
Installation | Server installation | I | I | P | R
| Software configuration | P | P | R | P
| Interface set-up and testing | I | I | P | R
| Analyzer(s) install | I | R | I | I
| Analyzer(s) verification | I | R | I | P
| Key operator training (Software & Analyzer) | I | R | I | P
Pre Go-live | Operator Training on Analyzer | I | R | I | P
Go-live | Go-live confirmation review | P | P | P | P
| Move from Test to Production | I | I | P | R
| Deploy analyzer(s) | I | P | I | R
| Monitor and troubleshoot as necessary | I | R | I | P
Post go-live | Continue to monitor and troubleshoot systems | I | P | I | R
| Conduct project de-brief | R | P | P | P
Roles
Responsible | Person responsible to perform the activity |  | R
Informed | Person kept informed on the status of the activity |  | I
Participate | Person who will be needed to participate in the activity |  | P
*KEY:
V PM | Vendor Project Manager
V OS | Vendor Onsite Support
V IT | Vendor IT
Customer | Customer Team

## Implementation Timeline
Single Site Installation Plan
Milestones | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | etc.
Contract Awarded
Contract Booked
Installation Preparation Meeting - On Site/Virtual
Project Development
Workflow Design
Weekly Communication Begins
Deliver Project Plan
Server Installation
Software Configuration
Interface Set-up and Testing
Analyzer(s) Install
Analyzer(s) Verification
Key Operator Training
Operator Training
Go-live Confirmation Review
Move from Test to Production
Deploy Analyzer(s) to Designated Sites
Other(s)

## Implementation Schedule
|  |  |  | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M
|  | Month | X
Location | # Analyzers
Site A |  | PW | IT | HI | V | V | VS | VS |  |  | T | T | T | T | T |  |  | GO
Prework | PW
Interface prep, install and testing | IT
Hardware Install | HI
Verification Studies | V
On Site Training | T
Go Live | GO
Additional Vendor Support | VS